## Backlog
| Project | usedcartrader.com
| Scrum Team | PO, Scrum Master, Development Team
| Created by | Product Owner
USER STORIES | Issue ID | Feature/Title | User Story Description | Story Points | Sprint | Epic
| UCT00X | Unregistered user can view listed cars and their prices | As an unregistered user, I want to view listed cars So that I can see the features and the prices of cars. | 5 | 1 | For a used car website, the target is to meet the wishes of users.
| UCT00X | Unregistered user can register on website | As an unregistered user, I want to register on the website, So that I can buy the listed cars and sell my own car. | 3 | 1
| UCT00X | Registered user can save his/her own car on the website | As a registered user, I want to save my cars on the website, So that I can get an instant valuation. | 5 | 1
| UCT00X | Registered user can save the favoritte advertisements | As a registered user, I want to save the favoritte adverts, So that I can easily return to these adverts later. | 3 | 2
| UCT00X | Registered user can save his/her searches to run again | As a registered user, I want to save my searches on the website, So that I can get notifications that match my search criteria. | 5 | 2
| UCT00X | Registered user can create adverts to sell his/her car | As a registered user, I want to create advertisement, So that I can sell my own car. | 8 | 2
| UCT00X | Registered user can save his/her personal and contact information | As a registered user, I want to save my personal and contact information, So that buyers and sellers can contact me. | 8 | 3
| UCT00X | Registered users can send message to sellers | As a registered user, I want to send message to sellers, So that I can chat with sellers. | 5 | 3
BUGS | Issue ID | Summary | Bug Description | Priority | Sprint
| UCT00X | When clicking on registration, website crashes. | Website crashes each time when clicking onregistration. Using the 10.28.99 build on a Win NT 4.0 (Service Pack 5) system. | Highest | 3
| UCT00X | Unregistered users are not able to view the prices of the cars. | When in unregistered mode, being able to see all the feaures of the cars, but not able to view the prices. Need to fix this bug. | Highest | 2

## Example Sub-tasks
QA Tasks | Dev Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test cases | Setting Up Dev Environment
Reviewing Test cases | Developing Programs
Setting Up Test Environment | Code Review
Creating Test data | Creating Unit Test Cases
Executing Manual Tests | Executing Unit Tests
Automation Setup | Merging Code
Automation Design | Creating Builds
Automating Test Cases | Fixing Bugs
Retesting Bugs
Regression Testing
Demo User Story
From here choose a few task for each user story.